## Gantt_Image1Format_Image2Conten
TASK | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Research Protocol | [16 empty] | Term Break
Protocol writing
Risk assessment
Research protocol presentation
Research Protocol Submission
WRITING
Introduction and Literature Review
Methodology
Results
Discussion
Data Analysis
Data Cleaning and Prelim analysis
Descriptive stats and visuals
Assumptions Testing
Complete Cases Analysis
Time to event analysis
Sensitivity analysis
Editing
First Section proofread
Supervisor review
Correction of feedback
Submission
Modules
Advanced Biostatistics
Changing Behaviour
Health Economics
Causal Inference
NCD Epidemiology
Contingency Time